## Summary
OFFICIAL SENSITIVE - WHEN COMPLETE | [7 empty] | BICC Portfolio Office
BOARD INVESTMENT COMMERICAL COMMITTEE TIER 1 PORTFOLIO REPORT
PART 1 - SUMMARY |  |  |  | Reporting Period |  | Qtr. Joined BICC Portfolio |  |  | New data being collected
Please select from the dropdown list. For GMPP the projects the start date has been completed for you.
Project / Programme Name |  |  |  | GMPP |  | Top 37
Project ID (DfT / IPA) |  |  |  | IUK top 40 |  | DfT Business Plan
DfT Group |  |  |  | Working Contact | Name
DfT Division |  |  |  |  | Telephone
Agency or Delivery Partner |  |  |  |  | Email
Senior Responsible Owner (SRO) | Name |  |  | Programme / Project Director | Name |  | Secondary PD (please list)
| Telephone |  |  |  | Telephone
| Email |  |  |  | Email
| SRO tenure start date |  |  |  | PD tenure start date
| Date of current SRO letter issued |  |  |  | Date if PD letter issued
| SRO tenure end date |  |  |  | PD tenure end date
| % of time spent on SRO role |  |  |  | % of time spent on PD role
| Has the SRO changed? |  | If SRO changed since last qtr, use dropdown to provide reason |  | Has the PD changed ? |  | If PD changed since last quarter, please use drop down to provide reason
| If yes, please state the reason |  |  |  | If yes, please state the reason
| SRO MPLA status |  | Please complete either MPLA / PLP section by using the dropdown |  | PD MPLA status |  | Please complete either MPLA / PLP section by using the dropdown
| SRO MPLA - if 'other' please describe |  |  |  | PD MPLA - if 'other' please describe
| SRO PLP status |  |  |  | PD PLP status
| SRO PLP - if 'other please describe |  |  |  | PD PLP - if 'other please describe
Strategic Alignment / Government Policy |  |  |  | Project Scope | [5 empty] | Please Complete and avoiding acronyms and technical language for GMPP projects this is used for the annual data publication
| Please complete using dropdown |  |  | Brief Project Description (please keep to a short sentence) | [5 empty] | Please Complete and avoiding acronyms and technical language for GMPP projects this is used for the IPA annual publication
Single Departmental Plan Alignment
|  |  |  | Risk Level (RPA) | Rating
Date
| Please complete strategic outcomes |  |  | Delivery Structure | Other
List Strategic outcomes (monetised and non-monetised benefits) |  |  |  | If other
Has project scope changed this quarter?
|  |  |  | Project Methodology |  | Please complete using drop down
If other please provide description
|  |  |  | Project Methodology | Primary Category |  |  |  |  | Please complete using drop down
[5 empty] | Secondary Category |  |  |  |  | Please complete using drop down
[5 empty] | Tertiary Category |  |  |  |  | Please complete using drop down
SRO Overall Delivery Confidence |  | Please complete using dropdown
SRO Overall Delivery Confidence (500 words) Please include: - Evidence for RAG, If the DCA has changed from the previous quarter – a brief explanation of why citing what specifically has changed since the last assessment - Progress update, particularly for those that are Amber/Red or Red citing what actions are being take to improve DCA - Finance comment, - Current and emerging risks and issues -
Please add date SRO approved report
SRO Sign-off date

## Finance & Benefits
OFFICIAL SENSITIVE - WHEN COMPLETE | [7 empty] | BICC Portfolio Office
BOARD INVESTMENT COMMERICAL COMMITTEE TIER 1 PORTFOLIO REPORT
PART 2 - FINANCIALS
Finance (£m)
SRO Finance Confidence |  |  | Please complete using dropdown
Source of Finance | Business Case used to source figures |  | Latest BICC approval point
| Name of source if not Business Case |  | Latest HMT approvals point
| Date of Business Case |  | Date of HMT approval point
| Version number of document used to source figures |  | Please add Business Case version number in cell C12
Date document approved by SRO
Does the project have a significant steel requirement with a capital value of £10m or above? |  |  |  | https://www.gov.uk/government/publications/procurement-policy-note-1615-procuring-steel-in-major-projects
Cost (£m to 1DP)
Real or Nominal | Baseline | real | Actual / Forecast | real
Index Year |  | As selected 'Real', please complete using dropdown
Deflator |  | As selected 'Real', please complete using dropdown
Source of finance |  | If 'other' describe
Calculated Net Present Value (NPV) for all projects, programmes if available
Forecast Project cost to closure (£m to 1DP)
Delegated Expenditure (£m to 1DP) | [6 empty] | RDEL or CDEL (please record AME spend in Non-Gov)
Resource - RDEL | Baseline: should reflect latest (approved) TAP figures. Forecast: should reflect expected spend; including change in internal budget allocation. | RDEL (one off new cost) | RDEL (recurring new costs) | RDEL (recurring old cost) | All RDEL (WLC) Total |  | Non-Gov (£m) both Revenue and Capital | Income (£m) both Revenue and Capital
Pre 2014/2015 | Baseline
Actual
2014/2015 | Baseline
Actual
2015/2016 | Baseline
Actual
2016/2017 | Baseline
Actual
Pre 2017/2018 | Budget |  |  |  | 0 | Spending Review Period 2015/16 - 2019/20
| Actual |  |  |  | 0
2017/2018 Spend on Profile | Yes/No |  |  |  | 0
2017/2018 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2022/2023 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2023/2024 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2024/2025 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2025/2026 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2026/2027 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2027/2028 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budget |  |  |  | 0
| Forecast |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 |  | 0 | 0
| Forecast | 0 | 0 | 0 | 0 |  | 0 | 0
Annual Steady state for recurring new costs
Year RDEL spend stops |  |  |  | Please complete using drop down
Project cost narrative (500 word limit)
Capital - CDEL | Baseline: should reflect latest (approved) TAP figures. Forecast: should reflect expected spend; including change in internal budget allocation. | CDEL (one off new cost) | CDEL (recurring new costs) | CDEL (recurring old cost) | All CDEL (WLC) Total
Pre 2014/2015 | Baseline
Actual
2014/2015 | Baseline
Actual
2015/2016 | Baseline
Actual
2016/2017 | Baseline
Actual
Pre 2017/2018 | Budget |  |  |  | 0 | Spending Review Period 2015/16 - 2019/20
| Actual |  |  |  | 0
2017/2018 Spend on Profile | Yes/No |  |  |  | 0
2017/2018 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2022/2023 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2023/2024 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2024/2025 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2025/2026 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2026/2027 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
2027/2028 | Budget |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budget |  |  |  | 0
| Forecast |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
Annual Steady state for recurring new costs
Year RDEL spend stops |  |  |  | Please complete using dropdown
Project cost narrative (500 word limit)
|  | Budget / Baseline | Forecast | Variance | Variance % | Total cost up to end of Spending Review Period | Budget / Baseline | Forecast | Issue with this bit now as this is not just spending round costs but includes total spend to end of SR you might want to remove or change what this calculation is.
Total WLC (RDEL) |  | 0 | 0 | 0 | 0% | Total WLC (RDEL) | 0 | 0
Total WLC (CDEL) |  | 0 | 0 | 0 | 0% | Total WLC (CDEL) | 0 | 0
Total WLC (Non-Gov) |  | 0 | 0 | 0 | 0% | Total WLC (Non-Gov) | 0 | 0
Total WLC |  | 0 | 0 | 0 | 0% | Total WLC | 0 | 0
PART 3 - BENEFITS
Benefits Management |  |  |  | Benefits Map |  | Please complete using dropdown
|  |  |  | Benefits Analysed |  | Please complete using dropdown
SRO Benefits Delivery RAG rating |  |  | Please complete using dropdown | Benefits Realisation Plan |  | Please complete using dropdown
Benefits | Baseline: should reflect latest (approved) TAP figures. Forecast: should reflect expected benefits | Gov.Cashable | Gov.Non-Cashable | Economic (inc.private partner) | Disbenefits UK Economic | All RDEL (WLC) Total
Pre 2014/2015 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2014/2015 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2015/2016 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
Pre 2017/2018 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2022/2023 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2023/2024 | Budget |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2024/2025 | Budget |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2025/2026 | Budget |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2026/2027 | Budget |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2027/2028 | Budget |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  | Benefits Cost Ratio (BCR) | Initial BCR |  |  | present Value Cost (PVC)
VfM category |  | Please complete using dropdown |  | Adjusted BCR |  |  | present Value Benefit (PVB)
For portfolio level analysis how should we calculate the net benefits position? | Deduct RDEL one off new costs? |  | Deduct RDEL Recurring new costs? |  | Deduct RDEL recurring old? |  | No deductions net benefits provided?
| Deduct CDEL one off new costs? |  | Deduct CDEL Recurring new costs? |  | Deduct CDEL recurring old? |  | Other - please describe
Benefits caveat (500 words)

## Resource
OFFICIAL SENSITIVE - WHEN COMPLETE | [7 empty] | BICC Portfolio Office
Part 4 - RESOURCE
Project Recourses
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project
SCS (PB3) |  |  |  | 0
SCS (PB2) |  |  |  | 0
SCS (PB1) |  |  |  | 0
Grade 6 (PB7) |  |  |  | 0
Grade 7 (PB6) |  |  |  | 0
FastSteam |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) |  |  |  | 0
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 0 | 0 | 0 | 0
Resource commentary
Project / Industry Capability and Capacity | Internal Project Team |  |  | SRO Skills RAG rating overall (Internal / External)
Function / Expertise | No. of public sector employees | No. of external contractors working on project | No. of vacancies / skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality
Legal, Commercial & Contract management | [5 empty] | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality
Project Delivery (including programme) | [5 empty] | N/A | Resource for this skill is not relevant for the project in question
Change Implementation
Technical
Industry Knowledge
Finance
Analysis
Communications, & Stakeholder Management
Other (please specify)
Other (please specify)
Total | 0 | 0 | 0
| The capability totals should add up to above resource table |  | Overall Assessment
Resource commentary

## Approval & Project Mileston
OFFICIAL SENSITIVE - WHEN COMPLETE | [6 empty] | BICC Portfolio Office
Part 5 - Approvals and Milestones
Approvals and Milestones
Project Stage |  | If other describe |  | This can only be completed once 'Delivery Structure' is complete on the Summary tab - Please complete once dropdown is available
Milestones (blue is mandatory) | Milestone date - as per latest TAP (or equivalent) | Latest Approved Baseline Date | Actual / Forecast Date | Type of milestone | Reason for movement / note
Approvals
SOBC - BICC Approval | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
SOBC - HMT Approval |  |  |  | Approval - HMT SOBC |  | Please add Original Baseline and/or Forecast date if either is missing
OBC - BICC Approval | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
OBC - HMT Approval |  |  |  | Approval - HMT OBC |  | Please add Original Baseline and/or Forecast date if either is missing
Planning Consents | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Pre-PIN Approval | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Pre-OJEU Approval | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Shortlisting BICC Approval | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Selection BICC Approval | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
FBC - BICC Approval | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
FBC - HMT Approval |  |  |  | Approval - HMT FBC |  | Please add Original Baseline and/or Forecast date if either is missing
1 - other approval point | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
2 - other approval point | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
3 - other approval point | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
4 - other approval point | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
5 - other approval point | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Approvals
Start of Project |  |  |  | Project Start Date |  | Please add Original Baseline and/or Forecast date if either is missing
Start on Construction/build | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Start of Operation | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Project End Date |  |  |  | Project End Date |  | Please add Original Baseline and/or Forecast date if either is missing
Business Case End Date |  |  |  | Business Case End Date |  | Please add Original Baseline and/or Forecast date if either is missing
1 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
2 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
3 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
4 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
5 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
6 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
7 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
8 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
9 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
10 - other key milestone | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Commentary / Notes (500 words)

## Assurance Planning
OFFICIAL SENSITIVE - WHEN COMPLETE | [6 empty] | BICC Portfolio Office
Part 5 - Assurance Planning
Assurance
Integrated Assurance and Approvals Plan (IAAP) | Date Created |  | Version Number
Date Revised
Milestones (blue is mandatory) | Milestone date - as per latest IAAP | Latest Approved Baseline Date | Actual / Forecast Date | Review Team Delivery Confidence Assessment (RAG | Reason for movement / note
Project Validation Review (PVR) (Project Initiation) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Gate 0 (Programme) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Gate1 or PAR (SOBC) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Gate 2 or PAR (OBC) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Gate 3 or PAR (FBC) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Gate 4 or PAR (Readiness for Service) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
Gate 5 or PAR (Project Closure & Lessons Learned) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
IPA Gate Exit | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
1 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
2 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
3 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
4 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
5 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
6 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
7 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
8 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
9 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
10 (Repeat assurance point, Assurance Action Plan (AAP), NAO, PAC, SGAR etc.) | [5 empty] | Please add Original Baseline and/or Forecast date if either is missing
IAAP SRO assessment of assurance activities
This section is fro the SRO to make an assessment of the Confidence / Quality element of the assurance reviews undertaken on the project and the projects / programme's response to any recommendations following these assurance activities (assurance action plans). This should be taken from the IAAP summary tab.
Assurance / Approvals
SRO Confidence / Quality RAG Rating - Assurance Activities | Internal
External
This section is fro the SRO to make an assessment of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme / project whichever is sooner.
Assurance / Approvals
SRO Confidence / Quality RAG Rating - Assurance Activities | Internal
External

## Dropdown
Quarter | Joining Qtr. (BICC &GMPP) | Classification | Entity format | Methodology | Category | Scope Changed | Monetised / Non Monetised Benefits | RAG | RAG 2 | RPA | Capability RAG | MPLA / PLP | PL Changes | Stage | Business Cases | Milestone Types | Finance figures format | Index Years | Discount Rate | Finance type | Yes/No | Years (Spend) | Years (Benefits) | Snapshot Dates | %age of time | AR Category | Project Lifecycle | Programme Lifecycle | Other | Start / Year end - FY |  | VFM | DfT Group | DfT Division | Agency | High Speed Rail Group | Rail Group | Roads, Devolution & Motoring | International, Security and Environment | Resource and Strategy | Non-Group | GMPP Annual Report Category | SDP
Q1 1516 | Q1 1112 | Official | Project | Waterfall | Asset Realisation | No | Monetised Benefit | Green | Green | Low | Green | Not Eligible - Master Builder | Career break | Concept | Strategic Outline Case | Project | Real | 1995 | 2% | Levy Control | Yes | No Spend | No Monetised Benefits | 2016-06-30 | 5% | Government Transformation and Service Delivery | Concept | Identification phase | Concept | 2016-03-31 | 3 | Very Poor | High Speed Rail Group | HS2 Phase 1 | DfT - DfTc | HS2 Phase 1 | Major Projects | Northern Transport Strategy | Airports Capacity Delivery | Group Commercial Services |  | Government Transformation and Service Delivery | Boosting Economic Growth and Opportunity
Q2 1516 | Q2 1112 | Official - Sensitive | Programme | Agile | Digital | Increase | Non-Monetised Benefit | Amber/Green | Amber | Medium | Amber | Not Eligible - Contractor | Consolidation of projects, resulting in one SRO / PD | Feasibility | Outline Business Case | Procurement | Nominal | 1996 | 2.1% | PFI | No | SOBC Costs being calculated | SOBC Monetised Benefits being calculated | 2016-09-30 | 10% | ICT | Feasibility | Definition phase | Feasibility | 2016-04-01 | 4 | Poor | Rail Group | HS2 Phase 2 | DfT - Driver and Vehicle Licensing Agency (DVLA) | HS2 Phase 2 | Passenger Service | Strategic Roads | Maritime |  |  | ICT | Building a One Nation Britain
Q3 1516 | Q3 1112 | Official - Commercial | Other | Hybrid | Decommissioning | Decrease | N/A | Amber | Red | High | Red | Not Eligible - Interim Appointment | Consolidation of SROs / PDs, resulting in one SRO / PD | Appraise & Select | Full Business Case | Other |  | 1997 | 2.2% | Public | - | Pre 2015/2016 | Pre 2015/2016 | 2016-12-31 | 15% | Infrastructure and Construction | Appraise & Select | Delivery phase | Appraise & Select | 2017-03-31 | 5 | Low | Roads, Devolution & Motoring | Rolling Stock & depot | DfT - Highways England | Rolling Stock & depot | Network Services | Motor, Freight & London | Energy, Technology & Innovation |  |  | Infrastructure and Construction | Improving Journeys
Q4 1516 | Q4 1112 |  |  | Hybrid - Programme (between projects) | Government Operations Reform (Transformation) |  |  | Amber/Red |  |  | N/A | Not Eligible - Leaving role | Departmental (or equivalent) Organisational change | Define and refine plan | Initial Gate Business Case (IGBC) |  |  | 1998 | 2.3% | Private |  | 2015/2016 | 2015/2016 | 2017-03-31 | 20% | Military Capability | Define and refine plan | Closure phase | Define and refine plan | 2017-04-01 | 6 | Medium | International, Security and Environment | Major Projects | DfT - Maritime and Coastguard Agency (MCA) |  |  | Local Authority |  |  |  | Military Capability | A Safe, Secure and Sustainable transport system
Q1 1617 | Q1 1213 |  |  | Hybrid - Programme (within Projects) | ICT Development and Refresh |  |  | Red |  |  |  | Not Eligible - Project Leaving GMPP | Directorate (or equivalent) Organisational change | Execute | Main Gate Business Case (MGBC) |  |  | 1999 | 2.4% | Other |  | 2016/2017 | 2016/2017 | 2017-06-30 | 25% |  | Execute (Delivery) | Benefits Realisation phase | Execute (Delivery) | 2018-03-31 | 7 | High | Resource and Strategy | Passenger Service | DfT - Driver and Vehicle Standards Agency (DVSA)
Q2 1617 | Q2 1213 |  |  | Hybrid - programme (between and within projects) | Infrastructure |  |  | Reset |  |  |  | Not Eligible - Agreed with IPA | End of loan / secondment from Other Government dept | Operate | PBC (or equivalent) |  |  | 2000 | 2.5% |  |  | 2017/2018 | 2017/2018 | 2017-09-30 | 30% |  | Operate | Other | Operate | 2018-04-01 | 8 | Very High | Non-Group | Network Services | DfT - HS2 Ltd
Q3 1617 | Q3 1213 |  |  |  | Military Capability | [6 empty] | Eligible - awaiting cohort | End of loan / secondment from Other Non-Government organisation | Embed in BAU. Review and lessons Learnt | On Hold |  |  | 2001 | 2.6% |  |  | 2018/2019 | 2018/2019 | 2017-12-31 | 35% |  | Embed in BAU. Review and lessons Learnt |  | Embed in BAU. Review and lessons Learnt | 2019-03-31 | 9 | Economically Efficient / Cost Saving |  | Northern Transport Strategy | Network Rail
Q4 1617 | Q4 1213 |  |  |  | Procurement | [6 empty] | Cohort 0 | End of SRO letter stated tenure | Completion Benefits realisation (steady state) | No Business Case |  |  | 2002 | 2.7% |  |  | 2019/2020 | 2019/2020 | 2018-03-31 | 40% |  | Completion Benefits realisation (steady state) |  | Completion Benefits realisation (steady state) | 2019-04-01 | 10 | Financially Positive |  | Strategic Roads | TfL
Q1 1718 | Q1 1314 |  |  |  | Public Service Delivery Reform (Transformation) | [6 empty] | Cohort 1 | End of temporary promotion | Other | No Business Case required |  |  | 2003 | 2.8% |  |  | 2020/2021 | 2020/2021 |  | 45% |  | Other |  | Identification phase | 2020-03-31 | 11 | No Category |  | Motor, Freight & London
Q2 1718 | Q2 1314 |  |  |  | Other | [6 empty] | Cohort 2 | Internal governance restructure |  | SOBC being developed |  |  | 2004 | 2.9% |  |  | 2021/2022 | 2021/2022 |  | 50% |  |  |  | Definition phase | 2020-04-01 | 12 | N/A |  | Local Authority
Q3 1718 | Q3 1314 | [10 empty] | Cohort 3 | Left due to not being an MPLA graduate |  |  |  |  | 2005 | 3% |  |  | 2022/2023 | 2022/2023 |  | 55% |  |  |  | Delivery phase | 2021-03-31 | 13 |  |  | Airports Capacity Delivery
Q4 1718 | Q4 1314 | [10 empty] | Cohort 4 | Left due to not being an PLP graduate |  |  |  |  | 2006 | 3.1% |  |  | 2023/2024 | 2023/2024 |  | 60% |  |  |  | Closure phase | 2021-04-01 | 14 |  |  | Maritime
Q1 1819 | Q1 1415 | [10 empty] | Cohort 5 | Left for new role in current department |  |  |  |  | 2007 | 3.2% |  |  | 2024/2025 | 2024/2025 |  | 65% |  |  |  | Benefits Realisation phase | 2022-03-31 | 15 |  |  | Energy, Technology & Innovation
Q2 1819 | Q2 1415 | [10 empty] | Cohort 6 | Left for new role in government |  |  |  |  | 2008 | 3.3% |  |  | 2025/2026 | 2025/2026 |  | 70% |  |  |  | Other | 2022-04-01 | 16 |  |  | Group Commercial Services
Q3 1819 | Q3 1415 | [10 empty] | Cohort 7 | Left for new role in private sector |  |  |  |  | 2009 | 3.4% |  |  | 2026/2027 | 2026/2027 |  | 75% |  |  |  | Define | 2023-03-31 | 17
Q4 1819 | Q4 1415 | [10 empty] | Cohort 8 | Left for new role on promotion in current department |  |  |  |  | 2010 | 3.5% |  |  | 2027/2028 | 2027/2028 |  | 80% |  |  |  | Categorise | 2023-04-01 | 18
| Q1 1516 | [10 empty] | Cohort 9 | Left for new role on promotion in government |  |  |  |  | 2011 | 3.6% |  |  | 2028/2029 | 2028/2029 |  | 85% |  |  |  | Prioritise | 2024-03-31 | 19
| Q2 1516 | [10 empty] | Cohort 10 | Life Cycle based change |  |  |  |  | 2012 | 3.7% |  |  | 2029/2030 | 2029/2030 |  | 90% |  |  |  | Balance | 2024-04-01 | 20
| Q3 1516 | [10 empty] | Cohort 11 | Maternity Leave |  |  |  |  | 2013 | 3.8% |  |  | 2030/2031 | 2030/2031 |  | 95% |  |  |  |  | 2025-03-31 | 21
| Q4 1516 | [10 empty] | Cohort 12 | Paternity Leave |  |  |  |  | 2014 | 3.9% |  |  | 2031/2032 | 2031/2032 |  | 100% |  |  |  |  | 2025-04-01 | 22
| Q1 1617 | [10 empty] | Cohort 13 | Post Rotation |  |  |  |  | 2015 | 4% |  |  | 2032/2033 | 2032/2033 | [6 empty] | 2026-03-31 | 23
| Q2 1617 | [10 empty] | Cohort 14 | Project transferred to other government entity |  |  |  |  | 2016 | 4.1% |  |  | 2033/2034 | 2033/2034
| Q3 1617 | [10 empty] | Cohort 15 | Retirement |  |  |  |  | 2017 | 4.2% |  |  | 2034/2035 | 2034/2035
| Q4 1617 | [10 empty] | Cohort 16 | Review recommended departure |  |  |  |  | 2018 | 4.3% |  |  | 2035/2036 | 2035/2036
| Q1 1718 | [10 empty] | Cohort 17 | Secondment outside Civil Service |  |  |  |  | 2019 | 4.4% |  |  | 2036/2037 | 2036/2037
| Q2 1718 | [10 empty] | Cohort 18 | Secondment within Civil Service |  |  |  |  | 2020 | 4.5% |  |  | 2037/2038 | 2037/2038
| Q3 1718 | [10 empty] | Cohort 19 | Temporary / Interim Assignment only | [5 empty] | 4.6% |  |  | 2038/2039 | 2038/2039
| Q4 1718 | [10 empty] | Cohort 20 | [6 empty] | 4.7% |  |  | 2039/2040 | 2039/2040
| Q1 1819 | [10 empty] | Other | [6 empty] | 4.8% |  |  | 2040/2041 | 2040/2041
| Q2 1819 | [17 empty] | 4.9% |  |  | 2041/2042 | 2041/2042
| Q3 1819 | [17 empty] | 5% |  |  | 2042/2043 | 2042/2043
| Q4 1819 | [20 empty] | 2043/2044 | 2043/2044
[22 empty] | 2044/2045 | 2044/2045
[22 empty] | 2045/2046 | 2045/2046
[22 empty] | 2046/2047 | 2046/2047
[22 empty] | 2047/2048 | 2047/2048
[22 empty] | 2048/2049 | 2048/2049
[22 empty] | 2049/2050 | 2049/2050
[22 empty] | 2050/2051 | 2050/2051
[22 empty] | 2051/2052 | 2051/2052
[22 empty] | 2052/2053 | 2052/2053
[22 empty] | 2053/2054 | 2053/2054
[22 empty] | 2054/2055 | 2054/2055
[22 empty] | 2055/2056 | 2055/2056
[22 empty] | 2056/2057 | 2056/2057
[22 empty] | 2057/2058 | 2057/2058
[22 empty] | 2058/2059 | 2058/2059
[22 empty] | 2059/2060 | 2059/2060
[22 empty] | 2060/2061 | 2060/2061
[22 empty] | 2061/2062 | 2061/2062
[22 empty] | 2062/2063 | 2062/2063
[22 empty] | 2063/2064 | 2063/2064
[22 empty] | 2064/2065 | 2064/2065
[22 empty] | 2065/2066 | 2065/2066
[22 empty] | 2066/2067 | 2066/2067
[22 empty] | 2067/2068 | 2067/2068
[22 empty] | 2068/2069 | 2068/2069
[22 empty] | 2069/2070 | 2069/2070
[22 empty] | 2070/2071 | 2070/2071
[22 empty] | 2071/2072 | 2071/2072
[22 empty] | 2072/2073 | 2072/2073
[22 empty] | 2073/2074 | 2073/2074
[22 empty] | 2074/2075 | 2074/2075
[22 empty] | 2075/2076 | 2075/2076
[22 empty] | 2076/2077 | 2076/2077
[22 empty] | 2077/2078 | 2077/2078
[22 empty] | 2078/2079 | 2078/2079
[22 empty] | 2079/2080 | 2079/2080
[22 empty] | 2080/2081 | 2080/2081
[22 empty] | 2081/2082 | 2081/2082
[22 empty] | 2082/2083 | 2082/2083
[22 empty] | 2083/2084 | 2083/2084
[22 empty] | 2084/2085 | 2084/2085
[22 empty] | 2085/2086 | 2085/2086
[22 empty] | 2086/2087 | 2086/2087
[22 empty] | 2087/2088 | 2087/2088
[22 empty] | 2088/2089 | 2088/2089
[22 empty] | 2089/2090 | 2089/2090
[22 empty] | 2090/2091 | 2090/2091
[22 empty] | 2091/2092 | 2091/2092
[22 empty] | 2092/2093 | 2092/2093
[22 empty] | 2093/2094 | 2093/2094
[22 empty] | 2094/2095 | 2094/2095
[22 empty] | 2095/2096 | 2095/2096
[22 empty] | 2096/2097 | 2096/2097
[22 empty] | 2097/2098 | 2097/2098
[22 empty] | 2098/2099 | 2098/2099
[22 empty] | 2099/2100 | 2099/2100
[22 empty] | Post 2100 | Post 2100

## GMPP
IPA ID Number
IPA ID Number 2
Dept
Main Reason for Joining GMPP
IPA DCA
IPA DCA Commentary
SRO ID
PD ID
GMPP Annual Report Category
Not currently being used
this data is from the GMPP that is IPA specific

## VERSION
version | Date | Editor | Notes
V0.1 | 2017-04-07 | Michelle Jennings | start of new template, added tabs and subsequent data fields any typos from old template in red. New tab added design for notes on format etc
V0.2 | 2017-04-10 | Michelle Jennings | added formula's and functions those in yellow need to be corrected - completed 13/04/217
V0.3 | 2017-04-13 | Michelle Jennings | added dropdown lists, prep for GMPP changes see benefits section - need to check with Andy Potthurst that this is how they will be collecting the information
V0.4 | 2017-05-17 | Michelle Jennings | finalised templates and updated printing options

## DESIGN
All cell colours where possible have been taken from the pallet or stand colour chart
Data Title boxes |  | Dark Teal Red - 0 Green - 128 Blue - 128 |  | Project Response Cell |  | Aqua Red - 204 Green - 228 Blue - 150 |  | BICC Portfolio Office Data Title | Blue, Accent 5, Dark 25% Red - 48 Green - 84 Blue - 150 | BICC Portfolio Office Data | Blue, Accent 5, Lighter 80% Red - 217 Green - 225 Blue - 242
New data being collected |  | Gold, Accent 4 Red - 225 Green - 195 Blue - 0 |  | Finance budget/forecast |  | Teal Red -135 Green - 191 Blue - 182
CELL BOARDERS | THICK WHITE
FONT | data cells | Arial - 11
| Title | Arial - 14
| Part /section title | Arial - 16
| colour | white or black
Summary tab - text box length | Strategic Alignment, Project Scope and short description | less than 5001 characters (350 words)
| project scope change and SRO RAG | less than 7001 characters (500 words) |  |  |  |  | To Note that some formulas have been copied over but without =IF
Summary Tab scope | (AND(OR(G35="increase",G35="decrease"),H35=""),"Please complete as scope change","")
Finance tab | note that the finance breakdowns do not allow negative figures (see Data validation) expect where applicable and are set for accounting (format cell).
Finance Tab source of Finance - BC or other document should be used not both. | (AND(C9="",C10="",D11=""),"Please complete source of finance figures",IF(OR(C9="",C10="",D11=""),"Please add Business Case version number in cell C12",IF(OR(C9="",C10="",D11=""),"Please complete only C9 or C10, not both","")))
Finance Tab Forecast project to end date (this formula checks the project and BC end dates against WLC. In short forecast project cost to end cannot be more than WLC) | (OR('Approval & Project Mileston'!BD29="",'Approval & Project Mileston'!D30=""),"",IF(AND('Approval & Project Mileston'!B29='Approval & Project Mileston'!B30,B23<>D80),"Cell B23 and Cell D80 MUST be the same due to the two END DATEs being the same",IF(AND('Approval & Project Mileston'!D29<'Approval & Project Mileston'!D30,B23=D80),"Cell B23 and Cell D80 MUST be different as the two END DATEs are different",IF('Approval & Project Mileston'!D29>'Approval & Project Mileston'!D30,"There is an error in the two END DATES Project End Date must not be after BC End Date - please relook at the dates",IF(D80<B23,"Forecast Project costs to closure must not be greater than Forecast WLC, please check","")))))
Finance Tab Annual steady state | (AND(OR(D44>0,D45>0,)),"Please complete annual steady state","")
Milestones and Assurance Tab | for the formula for checking the milestones dates use formula in cell 'c' adding =IF at the front and change the cell numbers |  |  |  | (OR(B9="",D9=""),"Please add Original Baseline and/or Forecast date if either is missing",IF(B9=C9,"Please delete Rebaseline as same as Original Baseline",IF(D9=B9,"",IF(AND(D9<>B9,G141=""),CONCATENATE(D9-B9," / ",IF(C9<>"",D9-C9,"-")," days change from the Original Baseline / Rebaseline - please provide reason if considered significant change. If Rebaselined, please provide reason"),IF(C9="",CONCATENATE(D9-B9," days change from the Original Baseline"),CONCATENATE(D9-B9," days change from the Original Baseline; ",D9-C9," days change from the rebaseline"))))))
Milestones Tab | Delivery Structure' dropdown is dependant on summary tab 'Project Methodology' dropdown |  | to create a dependent dropdown use this method -
Dates | to ensure that dates are only added to cells use the Data Validation and great than 01/01/1900
Project stage | This is an indirect dropdown |  |  | In the dropdown list tab name the list this needs to correspond to the delivery structure list
in summary select the dropdown in the normal way
in the approvals & project milestones select datavalidation and write =INDIRECT(Summary!G32)
https://www.ablebits.com/office-addins-blog/2014/09/30/dependent-cascading-dropdown-lists-excel/